## 7 Step Summary
Summarizing the 7 Steps
| Step 1 | Calculate - sprint duration | Final Capacity (in Hours)
| Step 2 | Create list of team members | Paul J. | 47.7
| Step 3 | Calculate team members' Allocations | Kalpesh P. | 47.7
| Step 4 | Calculate standard working hours/day | Carlos M. | 54.9
| Step 5 | Factors for consideration: - Team holiday - Individual planned vacation - Individual Partial day off | Satya S. (offshore) | 54.9
| Step 6 | Calculate ceremony time, other work (emails, etc) | Saurabh K. (offshore) | 47.7
| Step 7 | Calculate Focus Factor (Forecast velocity = Av. Vel/focus factor | Harini R. (offshore) | 33.3
|  |  | Jaswant C. (offshore) | 22.5
|  |  | Total ----------> | 308.7

## Story Points
1. Story Points
Sprint Velocity (---- Agents team)
Sprints (2 wk) SP
Sprint 1 | 34
Sprint 2 | 26
Sprint 3 | 32 | Capacity for Sprint 9 = 33 Story Points
Sprint 4 | 36
Sprint 5 | 30
Sprint 6 | 31
Sprint 7 | 39
Sprint 8 | 32
Average of last 6 Sprints = 33.33 Round off velocity (33)

## Pre-cap planning
Step 1 - Calc. sprint duration | [6 empty] | Step 2 - Calc. ---- team availability |  |  |  | Step 3 - Identify Allocation %
Sprint Calendar | [6 empty] | Team Member |  | Role |  | Team Member |  |  | Role | % Allocation
Week 1 | Mon | Tue | Wed | Thurs | Fri |  | Paul J. |  | Developer |  | Paul J. |  |  | Developer | 100%
| Sprint 1 |  | Day 1 | Day 2 (July 4) | Day 3 |  | Kalpesh P. |  | Developer |  | Kalpesh P. |  |  | Developer | 100%
Week 2 |  |  | 50 hrs | 0 hrs | 50 hrs |  | Carlos M |  | Developer |  | Carlos M |  |  | Developer | 100%
| Day 4 | Day 5 | Day 6 | Day 7 | Day 8 |  | Satya S. (offshore) |  | Developer |  | Satya S. (offshore) |  |  | Developer | 100%
Week 3 | 50 hrs | 50 hrs | 50 |  |  |  | Saurabh K. (offshore) |  | Tester |  | Saurabh K. (offshore) |  | Tester |  | 100%
| Day 9 | Day 10 | Sprint 2 |  |  |  | Harini R, (offshore |  | QA/Tester |  | Harini R, (offshore |  |  | QA/Tester | 75%
| 50 hrs | 50 hrs |  |  |  |  | Jaswant C. (offshore) |  | Tester |  | Jaswant C. (offshore) |  | Tester |  | 50%
Legends | Previous sprint |  | Future sprint
Current Sprint
Step 4 - Total standard hours per day calculated
[6 empty] | Team Member |  | Role | % Allocation | Hours/day |  | Hours/sprint
[6 empty] | Paul J. |  | Developer | 100 | 8 |  | 72
[6 empty] | Kalpesh P. |  | Developer | 100 | 8 |  | 72
[6 empty] | Carlos M. |  | Developer | 100 | 8 |  | 72
[6 empty] | Satya S. (offshore) |  | Developer | 100 | 8 |  | 72
[6 empty] | Saurabh K. (offshore) |  | Tester | 100 | 8 |  | 72
[6 empty] | Harini R, (offshore |  | QA/Tester | 75 | 6 |  | 54
[6 empty] | Jaswant C. (offshore) |  | Tester | 50 | 4 |  | 36
[6 empty] | xxxx Scrum Team ---------------------> |  |  |  | 50 |  | 450

## Impact Factors
FACTORS IMPACTING ACTUAL DEVELOPMENT & TESTING TIME
Ceremony Time | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
Ceremonies | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | Total Mins | Total Hours
Daily Scrum Call |  |  | 20 | Holiday | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  | 180 | 3
Grooming | 2019-07-05: 60; 2019-07-10: 60; 2019-07-16: 60 | 180 | 3
Sprint Planning - Day 1 | 2019-07-03: 120 | 120 | 2
Sprint Review/Demo | 2019-07-16: 120 | 120 | 2
Retrospective | 2019-07-16: 60 | 60 | 1
Grand Total: | [15 empty] | 660 | 11

## Capacity Planning
Calculating Ceremony Time |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
Resource name | Hrs/Day | Allocation | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | Sprint (hrs) | Ceremony Time (hrs) | Available Capacity (hrs) | Focus Factor | Final Capacity (hrs)
Paul J. | 8 | 100% | Previous Sprint |  | 8 | Holiday | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | Next Sprint |  |  | 64 | 11 | 53 | 90% | 47.7
Kalpesh P. | 8 | 100% |  |  | 8 |  | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 |  |  |  | 64 | 11 | 53 | 90% | 47.7
Carlos M. | 8 | 100% |  |  | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  |  | 72 | 11 | 61 | 90% | 54.9
Satya S. | 8 | 100% |  |  | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  |  | 72 | 11 | 61 | 90% | 54.9
Saurabh K. | 8 | 100% |  |  | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 |  |  |  | 64 | 11 | 53 | 90% | 47.7
Harini R. | 6 | 75% |  |  | 6 |  | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 |  |  |  | 48 | 11 | 37 | 90% | 33.3
Jaswant C, | 4 | 50% |  |  | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  |  | 36 | 11 | 25 | 90% | 22.5
Total Hrs ----> |  |  |  |  | 50 |  | 42 | 50 | 42 | 50 | 44 | 50 | 42 | 50 |  |  |  | 420 | 77 | 343 |  | 308.7
Next Steps: Feed into Capacity Planner add-on in Jira
Vacations
Deductions
Holiday

## Velocity
Sprint | Completed Story Points
Sprint 1 |  | 23
Sprint 2 |  | 29
Sprint 3 |  | 34
Sprint 4 |  | 10
Sprint 5 |  | 25
Sprint 6 |  | 30
Sprint 7 |  | 28
Average of last few Total number of
Story points accepted each Sprint
Last 6 Sprints Completed Story Points
Total = 157 Story Points
Velocity = 157/6 = 26 Story Points

## Commitment Reliability
CMAS team reliability vis a vis commitment (Measurement Unit = Story Pts)
Total # of story points completed vs committed
Commitment Reliability
xxxx PROJECT TO-DATE |  |  |  |  | Level | From | To | Total
Sprint data |  |  | Formula | Result | Red | 0% | 80% | 80%
Sprint | Committed | Accepted |  | CR | Amber | 81% | 90% | 15%
Sprint 2 | 29 | 29 |  | 100% | Green | 91% | 100% | 5%
Sprint 3 | 34 | 34 | (Accepted/Committed)*100 | 100%
Sprint 4 | 16 | 10 |  | 63%
Sprint 5 | 30 | 25 |  | 83%
Sprint 6 | 45 | 30 |  | 67%
Sprint 7 | 30 | 29 |  | 97%

## Capacity utilization
Capacity Utilization (Measurement Unit = Efforts Estimation)
xxxx PROJECT TO-DATE
Sprint data |  |  | Formula | Result
Sprint | Available | Committed |  | Utilization
Sprint 2 | 220 | 130 |  | 59%
Sprint 3 | 240 | 190 | (Committed/Available)*100 | 79%
Sprint 4 | 280 | 140 |  | 50%
Sprint 5 | 230 | 200 |  | 87%
Sprint 6 | 243 | 221 |  | 91%
Sprint 7 | 226 | 220 |  | 97%
Effort Hours

## Estimation Variance
Effort Estimation Variance (Measurement unit = Efforts Estimation)
xxxx PROJECT TO-DATE
Sprint data |  |  | Formula | Result
Sprint | Estimated | Actual | Over Estimation | Variance
Sprint 2 | 130 | 40 | (E-A/E)*100 | 69%
Sprint 3 | 190 | 190 |  | 0%
Sprint 4 | 140 | 200 |  | 43%
Sprint 5 | 200 | 189 | Under Estimation | 6%
Sprint 6 | 221 | 178 | (A-E/E) * 100 | 19%
Sprint 7 | 220 | 215 |  | 2%
Estimated Effort Hours |  |  | E = Estimated Effort
A = Actual Effort

## Scope Change
Product backlog items added/removed from sprint scope AFTER sprint start (Measurement unit = Story Points)
xxx PROJECT TO-DATE
Sprint data |  |  |  | Formula | Result
Sprint | Committed | Added SP | Descoped SP | De-scoped | Variance
Sprint 2 | 29 | 0 | 10 | (D/C)*100 | 34%
Sprint 3 | 34 | 0 | 0 |  | 0%
Sprint 4 | 16 | 23 | 0 |  | 144%
Sprint 5 | 30 | 0 | 15 | Scope Increased | 50%
Sprint 6 | 45 | 0 | 0 | (A/C) * 100 | 0%
Sprint 7 | 30 | 0 | 0 |  | 0%
Scope as story points |  |  |  | D= Removed Story Points A = Added story points C=Committed story points

## Defect Leakage
Total number of defects detected AFTER sprint closure (Measurement unit = Defect count
xxxx PROJECT TO-DATE
Sprint data |  |  | Formula | Result
Sprint | Defects during sprint | Defects Post Sprint | ((Post sprint Defect count/Defects detected during sprint) * 100 | Defect Leakage
Sprint 2 | 20 | 1 |  | 5%
Sprint 3 | 10 | 0 |  | 0%
Sprint 4 | 30 | 4 |  | 13.33%
Sprint 5 | 5 | 1 |  | 20%
Sprint 6 | 12 | 4 |  | 33.33%
Sprint 7 | 22 | 6 |  | 27.27%
Scope as story points

## Backlog Health
Total story pts avlble in prod. Backlog compared w/ Av. Velocity
CMAS TEAM
Average Velocity | Product backlog groomed (DOR) story
26.17 | 20
Health Slabs
Less than avg. velocity
Meets avg. velocity
Meets twice avg. velocity
Meets three-times avg. velocity

## Dynamic scope option
Dynamic Scope option ("change for free")
1. After each iteration, sponsor may add new feature to backlog, but only after another feature of equal or greater size is removed
2. Above option can be so appealing that it may even give proj team sufficient leverage to renegotiate FFP constraints
FFP: Firm Fixed Price
Note: could this be source of frustration w/ problem customer??